## Martin Hawes - Gantt
			Week:
Task ID	Task	Predecessor	1	2	3	4	5	6	7	8	9	10	11	12	13
A	Work-stealing Research
B	Mandelbrot Set Explanation
C	Language/Tools Research
D	Design of algorithm	A,B,C
E	Non-Concurrent Algorithm	D
F	Concurrent Algorithm	D
G	Analysis	E,F
H	Reflection	G